## Sheet1
Risk Category | Risk Factor | Risk Description | Source/Reference
Construction | Supply chain disruptions | Delays in materials delivery (steel, concrete) due to logistics or global shortages. | https://learninglegacy.crossrail.co.uk/documents/risk-management-crossrail/
Environmental | Extreme weather events | Heavy rain, storms, or flooding disrupting construction schedules. | https://www.tideway.london/media/4635/tideway-sustainability-report-2019.pdf
Technical | Design errors | Errors in bridge load calculations or structural designs requiring redesign or delay. | https://doi.org/10.1016/j.proeng.2016.04.055
Construction | Equipment failure | Crane, piling rig, or scaffolding failures delaying key activities. | https://crossriverrail.qld.gov.au/
Safety | On-site accidents | Worker injuries from falls, equipment mishandling, or lifting operations. | https://www.hse.gov.uk/construction/
Cost | Budget overruns | Cost escalation from material prices, rework, or inflation. | PMBOK 7th Edition, Cost Risk Management Chapter
Regulatory | Planning permission delays | Delays securing environmental or local authority permits. | https://www.hs2.org.uk/building-hs2/health-safety/
Environmental | Contaminated ground conditions | Unexpected contamination (e.g., old industrial sites) requiring remediation. | https://www.tideway.london/
Geotechnical | Poor soil conditions | Unstable foundations causing re-engineering of pile designs. | https://ascelibrary.org/
Construction | Interface risk | Clashes between different contractors’ scopes (e.g., roadworks vs. bridgeworks). | https://learninglegacy.crossrail.co.uk/
Procurement | Subcontractor insolvency | Collapse of a major subcontractor mid-project. | https://www.constructionnews.co.uk/
Technical | Innovative technology risk | New construction methods (e.g., modular bridge components) failing in practice. | https://www.ice.org.uk/
Environmental | Waterway navigation risks | Construction equipment or debris impacting river or canal traffic. | https://www.tideway.london/
Schedule | Late design approvals | Slippage due to slow design reviews or value engineering iterations. | https://doi.org/10.1016/j.proeng.2017.09.760
Political / Legal | Community objections or legal injunctions | Public resistance delaying construction through legal challenges. | https://www.tideway.london/